## Slide 1
Bio-ortogonal catalysis for cancer therapy
IBEC Presentation
Mid-Term Check Meeting
Edinburgh, 5th June 2019
Institute for Bioengineering of Catalonia
Nanoscopy for nanomedicine group

## Slide 2
Institution description

## Slide 3
Institution description

## Slide 4
Research group

## Slide 5
Research group
THERACAT team
ESR6-TUE: Manos Archontakis
Contract start date: 01/03/19
Contract end date: 28/02/22
Coordinator and supervisor: Lorenzo Albertazzi
ESR7-IBEC: Alis Olea
Contract start date: 16/10/18
Contract end date: 15/10/21
Project Manager: Rosa Miralles

## Slide 6
Role within the network
Research
WP4: Prodrugs design and synthesis
Task 4.2. Synthesis of fluorescent dyes such (rhodamines, cyanines) protected with propargyl/allyl groups (IBEC-ESR7). Started
Task 4.3. Spectroscopic (bulk) and microscopic evaluation (single molecule) study of catalysis (EDI, IBEC-ESR7).
MS7. Synthesis of the first prodye. Month 18 D4.2. Set of 2-3 fluorescent prodyes. Month 28
WP5: In vitro delivery and imaging
Task 5.2. Fluorescence and super resolution optical imaging of carriers’ interactions with cancer cells (IBEC-ESR7, TUE).
Task 5.3. Test the efficiency of prodrug conversion in 2D and 3D cancer models (BGX, TUE, BAS, IBEC-ESR7).
MS10. Establishments of the protocol for super resolution imaging in cells. Month 18
D5.2. Description of the structure-activity relations of the material-cell interactions. Month 30
WP6: In vivo evaluation
Task 6.3. Use intravital optical and PET imaging to study catalyst localization and efficacy (BGX, TUE, BAS, IBEC-ESR7).

## Slide 7
Role within the network
Training Events
TE1 – Introducing the THERACAT Network & How to plan and start a PhD. COMPLETED – March 25-29,2019
General introduction & introduction of the training programme
Skills to start a successful PhD
TE3 – Drug delivery & microscopy. Month 24
The power of microscopy techniques in biomedical research: principles and challenges
TE5 – Getting ready for the next career step. Month 36
Searching for post-doc and setting the path for academic careers
Secondments at IBEC
ESR3-TEVA. Month 18 – 21 (4 months)
ESR8-TUE. Month 21 – 24 (4 months)
ESR9-BGX. Month 36 – 39 (4 months)
ESR13-TAU (Satchi-Fainaro). Month 21 – 24 (4 months)
Organisation of Network Meetings & Conference
Kick-off Meeting. Barcelona. May 31st, 2018.
Meeting 3. Month 36. Barcelona. February 2021.
THERACAT conference. Month 42. Barcelona. August 2021.
Final Meeting. Month 48. Barcelona. February 2022.
Member of Assessment Commission 3 (BAS, IBEC, BGX, TAU-a)
Fellows: ESR3, ESR8, ESR11, ESR12, ESR13